## Sheet1
Site Level Validation
S/N | Items | Legacy EMR | NigeriaMRS | Remarks
1 | Total number of Patients | 141 | 136
2 | Total number of Pharmacy encounter | 981 | 979
3 | Total number of Laboratory encounter | 177 | 177
4 | Total number of Care Card encounter | 1010 | 1008
5 | Calculated TX_CURR (28 days) | 69
6 | Count of TX_NEW (October 2020) | 3
Patient Level Validation
|  | Patient ID: 17991 |  | Patient ID: 17960 |  | Patient ID: 17717 |  | Patient ID: 17710 |  | Patient ID: 17705 |  | Patient ID: 17830 |  | Patient ID: 17767 |  | Patient ID: 17770 |  | Patient ID: 18344 |  | Patient ID: 18391
S/N | Items | Legacy EMR | New NMRS | Legacy EMR | New NMRS | Legacy EMR | New NMRS | Legacy EMR | New NMRS | Legacy EMR | New NMRS | Legacy EMR | New NMRS | Legacy EMR | New NMRS | Legacy EMR | New NMRS | Legacy EMR | New NMRS | Legacy EMR | NMRS
A | Ramdomly seclect 10 migrated clients records, for each of the selected patients, count for the following details in both the legacy EMR and NMRS
1 | Total number of Pharmacy encounter | 13 | 13 | 28 |  | 47 |  | 36 |  | 44 |  | 51 |  | 64 |  | 38 |  | 36 |  | 3
2 | Total number of Laboratory encounter | 2 | 2 | 2 |  | 2 |  | 3 |  | 3 |  | 0 |  | 2 |  | 4 |  | 1 |  | 0
3 | Total number of Care Card encounter | 14 | 14 | 7 |  | 15 |  | 8 |  | 11 |  | 13 |  | 16 |  | 10 |  | 10 |  | 1
4 | Patient status | ART Start |  | ART Transfer In |  | ART Start |  | ART Restart |  | ART Transfer In |  | ART Transfer In |  | ART Start |  | ART Transfer In |  | ART Start |  | ART Transfer In
B | For each of the randomly selected patients above , compare the following values between the legacy EMR and the NMRS
1 | Date of First encounter | 2012-11-20 | 2012-11-20 | 2018-09-24 |  | 2016-01-01 |  | 2016-03-22 |  | 2017-10-10 |  | 2018-11-19 |  | 2018-03-26 |  | 2018-04-09 |  | 2019-12-05 |  | 2020-09-01
2 | Date of Last encounter | 2020-08-05 | 2020-08-05 | 2020-06-09 |  | 2020-09-01 |  | 2020-09-01 |  | 2020-08-26 |  | 2020-06-16 |  | 2020-08-04 |  | 2020-09-02 |  | 2020-08-11 |  | 2020-09-01
3 | Date of first ARV pickup from the current facility | 2012-11-20 | 2012-11-20 | 2018-09-24 |  | 2016-01-01 |  | 2016-03-22 |  | 2017-10-10 |  | 2018-11-19 |  | 2018-03-26 |  | 2018-04-09 |  | 2019-12-05 |  | 2020-09-01
4 | First documented regimen | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+EFV(600mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg)
5 | Last documented regimen | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+EFV(600mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg) |  | TDF(300mg)+3TC(300mg)+DTG(50mg)
6 | Date of last lab encounter | 2019-12-24 |  | 2020-01-07 |  | 2020-03-18 |  | 2019-12-10 |  | 2020-07-07 |  | Nil |  | 2019-12-03 |  | 2020-03-18 |  | 2020-06-17 |  | Nil
7 | Date of first lab encounter | 2019-09-19 |  | 2019-08-29 |  | 2019-11-06 |  | 2018-12-12 |  | 2019-10-03 |  | Nil |  | 2019-09-11 |  | 2018-04-24 |  | 2020-06-17 |  | Nil
8 | Date of last documented viral load (if available) | 2020-01-29 |  | 2020-01-29 |  | 2020-05-14 |  | 2020-01-29 |  | 2020-08-24 |  | Nil |  | 2020-03-03 |  | 2020-05-14 |  | 2020-07-28 |  | Nil
9 | Last documented viral load result | 40 |  | 40 |  | 20 |  | 20 |  | 20 |  | Nil |  | 20 |  | 20 |  | 42 |  | Nil
10 | Date of first care card encounter | 2012-11-20 |  | 2018-09-24 |  | 2016-01-01 |  | 2016-03-22 |  | 2017-10-10 |  | 2018-11-19 |  | 2018-03-26 |  | 2018-04-09 |  | 2019-12-05 |  | 2020-09-01
11 | Date of last care card encounter | 2020-08-05 |  | 2020-06-09 |  | 2020-09-01 |  | 2020-07-28 |  | 2020-08-26 |  | 2020-06-16 |  | 2020-08-04 |  | 2020-09-02 |  | 2020-08-11 |  | 2020-09-01
12 | ART start date (if documented) | 2012-11-20 |  | 2018-09-24 |  | 2016-01-01 |  | 2016-03-22 |  | 2017-10-10 |  | 2018-11-19 |  | 2018-03-26 |  | 2018-04-09 |  | 2019-12-05 |  | 2020-09-01